## Day 1 - 25 March
Time | Level | Location | Task | Site Observations | Recording observations / duration | General observations | links | video
10:31 | 6 | Room 4 - Wall 2A | Framing studs | Bottom and top track already done, walls 5, 6, 7 already done previous day | Start timelapse 1 | Board size: 90x270 | https://youtu.be/kLcyjJaWoJs | 0.52 min
10:37 | 6 | Room 4 - Wall 2A | Measure board size from studs by hand |  |  | Room height 270m |  | 26 mins real
10:38 | 6 | Room 4 - Wall 2A | Measure and cut board + sand border |  |  | 2 faster workers and 2 slower ones -the fast ones place first side of gypsum and the slow the second side
10:41 | 6 | Room 4 - Wall 2A | Place board on studs and drill |  |  | 5 drills per stud approx.
10:43 | 6 | Room 4 - Wall 4A | Secure stud to bottom and top track |  |  | use short staircase to drill to top track
10:44 | 6 | Room 4 - Wall 4A | Measure length wall
10:45 | 6 | Room 4 - Wall 4A | Measure and cut board + sand border |  |  | 2 nail types: one longer than the other
10:48 | 6 | Room 4 - Wall 4A | Place board on studs and drill
10:49 | 6 | Room 4 - Wall 4A | Change nail type and measure on wall
10:50 | 6 | Room 4 - Wall 4A | Measure and cut board + sand border |  |  | Mark centerline for drilling in the board
10:53 | 6 | Room 4 - Wall 4A | Place second board layer and drill |  |  | use ladder and use board lift tool
10:55 | 6 | Room 4 - Wall 2A | Measure wall 1 for second layer
10:56 | 6 | Room 4 - Wall 2A | Measure and cut board + sand border |  |  | Rests are thrown away - cut in three parts to reduce space
11:00 | 6 | Room 4 - Wall 2A | Place second board layer |  |  |  | https://www.youtube.com/watch?v=88FpRH_O0cI | 2.05 min
11:01 | 6 | Room 4 - Wall 2A | Drill layer 2 to layer 1 |  |  |  |  | 61.5 mins real
11:02 | 6 | Room 4 - Wall 3 Kitchen | Measure and cut studs |  |  | height 1,20m
11:08 | 6 | Room 4 - Wall 3 Kitchen | Place bottom and top studs |  |  | use auxiliary diagonal studs
11:14 | 6 | Room 4 - Wall 3 Kitchen | Measure and mark kitchen studs |  |  | Coordination: general 15 minutes with all workers, management coordination meeting with subs 1 or 2 hours per week
11:17 | 6 | Room 4 - Wall 3 Kitchen | Measure track and cut
11:19 | 6 | Room 4 - Wall 3 Kitchen | Create stud L shape
11:22 | 6 | Room 4 - Wall 3 Kitchen | Finished L with auxiliary studs - go find backing material for kitchen
11:26 | 6 | Room 4 - Wall 2A | Measure position and drill 2 backing plates to wall 1
11:29 | 6 | Room 4 - Wall 2A | Measure and place third layer on top of wall 1
11:30 | 6 | Room 4 - Wall 2A | Drill wall 1 board, mark centerline to drill and secure to middle stud with long nails
11:35 | 6 | Room 4 - Wall 3 Kitchen | Measure and cut short boards + sand border side A
11:37 | 6 | Room 4 - Wall 3 Kitchen | Position and drill short wall side A
11:39 | 6 | Room 4 - Wall 3 Kitchen | Cut additional stud and secure small walls diagonally side A
11:48 | 6 | Room 4 - Wall 3 Kitchen | Measure, cut short boards +sand border sideB
11:50 | 6 | Room 4 - Wall 3 Kitchen | Position and drill short wall side B
11:52 | 6 | Room 4 - Wall 3 Kitchen | Take out the two diagonal auxiliar studs and place top corner auxiliar stud
11:54 | 6 | Room 4 - Wall 4 Bath - 4B | Measure and cut top track
11:55 | 6 | Room 4 - Wall 4 Bath - 4B | Positiona and drill top track to concrete slab
11:59 | 6 | Room 4 - Wall 4 Bath - 4B | Done - Lunch break |  | timelapse 1 finish
12:35 | 6 | Room 4 - Wall 2B | Finish break, start clean up and position and drill top track |  |  |  | https://youtu.be/B1uJCkkylKQ
12:48 | 6 | Room 4 - Wall 1 | Measure studs position, move materials, drill studs to bottom track | 4 vertical studs | Start timelapse 2
12:53 | 6 | Room 4 - Wall 1 | Drill studs to top track |  | 2:03
12:55 | 6 | Room 4 - Wall 1 | Move ladder, materials, and clean up | to room 6 | 15:06
13:10 | 6 | Room 6 | Set up materials and clean up |  | 9:08
13:19 | 6 | Room 6 - Walls sector A | Redo layout stronger on the floor and roof | use laser to align vertical studs in walls | 14:26
13:34 | 6 | Room 6 - Walls sector A | Measure stud position, cut studs and place each: 1 vertical, 2 horizontal to floor between doors, 3 horizontal to floor in corner, 4, horizontal bottom track | one by one measure, cut, and place | 11:33 | Studs:ER 70 ERGOnomic Gyproc
13:45 | 6 | Room 6 - Walls sector A | Place and drill top track to concrete slab and other vertical stud |  | 10:51 |  |  | 1h 44m
13:56 | 6 | Room 6 - Walls sector A | Go find wood studs for doors reinforcements | materials not at hand | 18:30 |  |  | 3.28 video
14:15 | 6 | Room 6 - Walls sector A | cut wood frames and place vertical studs | 4 in total, at the sides of both doors | 9:48
14:24 | 6 | Room 6 - Walls sector A | measure and cut wood horizontal structure for doors (measure first and then join to studs) |  | 12:31 | door height 1:20m | https://youtu.be/_zEHzi-eBRA
14:37 | 6 | Room 6 - Walls sector A | Place and drill 4 vertical wood studs and 4 short studs in door dintel + 10 minute break |  | 11:14 |  |  | 29 minutos
14:48 | 6 | Room 6 - Walls sector A | Measure and cut board + sand border |  | 2:00 |  |  | 00: 58 video
14:50 | 6 | Room 6 - Walls sector A | Place and drill boards on door side, coordination in the middle with another worker for next week task | place whole board and cut out the doors in position | 50:16
15:40 | 6 | Room 6 - Walls sector B | Measure and cut studs |  | 3:28
15:44 | 6 | Room 6 | Done for the day | 1 person only
Another worker on room 5 (big) working alone walls in that room.
14:06 | 7 | Room 4 | Layout | 1 person, last room of its type layout, worker seems to know masurements by heart
14:30 | 7 | Room 4 | Done layout | layout measures follow the core of the bathroom (which has prefabricated drywall walls) and will conditionate the dimensions of the kitchen for example | Woker mentioned that because it was only one person it was slower to hold the chalkline, layout done measuring by hand and with laser guide. | Layout based on how the kitchen fits to bathroom, by level 7 the worker does not need to watch the drawings almost, just uses ruler and laser, no total station. There are main marks on the floor where the main walls should be and then uses the prefab walls reference

## Day 2 - 26 March
Time | Level | Location | Task | Site Observations | Recording observations / duration | General observations | links | video duration
7:05 | 6 | Room 6 - Wall 1 & 2 | 4 studs cut and placed |  |  |  | https://youtu.be/bQyxDATfJzA | 3.13 min
7:14 | 6 | Room 6 - Wall 2 | Place vertical studs | 4 studs | Start timelapse 1 |  |  | 1h 36mins
7:16 | 6 | Room 6 - Wall 2 | Measure and cut board + sand border | 1 sector from wall until first stud
7:18 | 6 | Room 6 - Wall 1 | Place board on studs and drill | fix the stud at the same time
7:23 | 6 | Room 6 - Wall 3 | Cut and place bottom track for duct | [7 empty] | videos day 2
7:34 | 6 | Room 6 - Wall 3 | Place vertical studs duct | Left room to find stud for 2 minutes | [6 empty] | video 5 | https://youtu.be/bQyxDATfJzA
7:39 | 6 | Room 6 - Wall 3 | Measure and cut board + sand border | [7 empty] | video 6 | https://www.youtube.com/watch?v=OYQYCvmtkHM
7:43 | 6 | Room 6 - Wall 3 | Place board on studs and drill (larger side) | [7 empty] | video 7 | https://youtu.be/q_-UbOdsElk
7:46 | 6 | Room 6 - Wall 3 | Measure for side of duct one, cut board and sand | Through extra material | 2:58 | [5 empty] | video 8 | https://youtu.be/P0P5wRA7SC4
7:49 | 6 | Room 6 - Wall 3 | Place board on side of duct and drill and make hole for duct |  | 3:29
7:52 | 6 | Room 6 - Wall 3 | Make sure wall is plumb and sand corner |  | 2:01
7:54 | 6 | Room 6 - Wall 2 | Place full board and drill to stud | adjust stud position to where board ends, rework take out nails that didn't went through, about 10 seconds | 5:42
8:00 | 6 | Room 6 - Wall 2 | Measure and cut board + sand border | For portion to finish after 90cm full board, rework, wrong cut of board need to through it and get another | 2:36
8:03 | 6 | Room 6 - Wall 2 | Measure and cut board + sand border | small section | 1:56
8:05 | 6 | Room 6 - Wall 2 | Drill small section to studs | Found two broken studs | 1:33 | 1 full bucket of waste every 2-3 days (750kg max each bucket) |  | video 6 - | 0:57
8:06 | 6 | Room 6 - Wall 1 | Measure and place vertical studs (front part of wall 1 L) |  | 2:33 | 13 nails vertically approx |  | https://www.youtube.com/watch?v=OYQYCvmtkHM
8:09 | 6 | Room 6 - Wall 1 | Measure and cut board + sand border (front part of wall 1 L) |  | 1:11
8:10 | 6 | Room 6 - Wall 2 | Place full board and drill to stud | studs not drilled to top or bottom track | 4:00
8:14 | 6 | Room 6 - Wall 2 | Drill stud to top track |  | 0:26
8:14 | 6 | Room 6 - Wall 1 | Get board place in position and drill to studs | Full board, use board lifter for help, rework: take out 3 nails wrongly drilled approx 30 seconds | 5:44
8:20 | 6 | Room 6 - Wall 1 | Measure and cut board (complement after full board in front part) |  | 0:45
8:21 | 6 | Room 6 - Wall 1 | Place and drill board w/lifter; measure 90 degrees |  | 2:07
8:23 | 6 | Room 6 - Wall 1 | Done sector wall 1, start set up for the other sector in the floor, rearrange materials, take out auxiliary rails on other side of room
9:00 | 6 | Room 6 | Break
9:30 - 11:50 and 12:30 - 3 |  |  | Keep recording progress on video - at 3pm the other sector in the floor done |  |  |  |  | https://www.youtube.com/watch?v=q_-UbOdsElk |  | 3:13 video
| 6 | Room 5 - Area 1 - only time check no video
8:33 | 6 | Room 5 - Wall 1 | Drill top track wall 1 | Bottom track already instaled and right stud done | 1:29
8:34 | 6 | Room 5 - Wall 1 | Side stud drill to concrete |  | 2:13
8:37 | 6 | Room 5 - Wall 1 | Measure bottom track, place and drill vertical studs first all to the bottom and then to the top | 6 studs, use laser to make sure they are in angle, some holes cut in studs for isntallations | 10:25
8:47 | 6 | Room 5 - Wall 2 | Measure and cut bottom track |  | 1:12
8:48 | 6 | Room 5 - Wall 2 | Drill track to floor slab |  | 1:05
8:49 | 6 | Room 5 - Wall 2 | Place side vertical stud and drill to concrete |  | 1:05
8:50 | 6 | Room 5 - Wall 2 | Place top track on roof wall |  | 1:26
8:52 | 6 | Room 5 - Wall 2 | mark bottom track to set number of vertical studs, place 6 studs in position and then drill one by one first to bottom track and then to top | check with laser they are at angle | 9:20
9:01 | 6 | Room 5 | Breakfast break
9:30 | 6 | Room 5 | Back from break | for ducts you need to alternate and put the board first to be able to drill stud to board
9:45 | 6 | Room 5 - Wall 2 | Cut and place 1 section of drywall |  | 1:07
9:46 | 6 | Room 5 - Wall 3 | Measure and cut bottom track for duct | 4 vertical studs | 13:29
9:59 | 6 | Room 5 - Wall 3 | Place bottom tracj and vertical studs for duct and drill |  | 3:03
10:02 | 6 | Room 5 - Wall 3 | Measure and cut board for duct (front) |  | 6:43
10:09 | 6 | Room 5 - Wall 3 | Place and drill board front side duct, make cuts on board for installations with saw |  | 1:58
10:11 | 6 | Room 5 - Wall 3 | Measure and cut board for side of duct, place it and drill |  | 0:38
10:11 | 6 | Room 5 - Wall 3 | Go get board and place it on drywall table |  | 1:33
10:13 | 6 | Room 5 - Wall 3 | Measure and cut board - second layer side duct |  | 0:54
10:14 | 6 | Room 5 - Wall 3 | Drill second layer side board to the first one on the side of duct |  | 0:31
10:14 | 6 | Room 5 - Wall 3 | Measure and cut board third layer side of duct |  | 0:05
10:15 | 6 | Room 5 - Wall 3 | Transport board from table to position (small board for duct) |  | 2:16
10:17 | 6 | Room 5 - Wall 3 | Place and drill third layer to the previous |  | 2:33
10:19 | 6 | Room 5 - Wall 3 | Measure, cut, and drill horiontal stud to roof |  | 1:07
10:20 | 6 | Room 5 - Wall 3 | Measure second side of wall 3 duct on the floor |  | 1:25
10:22 | 6 | Room 5 - Wall 3 | Measure and cut bottom track for second side |  | 1:28
10:23 | 6 | Room 5 - Wall 3 | Drill bottom track to concrete floor |  | 1:32
10:25 | 6 | Room 5 - Wall 3 | Drill vertical stud wall 3 part 2 |  | 2:03
10:27 | 6 | Room 5 - Wall 3 | Grab and place two vertical studs |  | 2:52
10:30 | 6 | Room 5 - Wall 2 | Place and drill to vertical studs, bottom and top track full board | use ladder for top track | 0:37
10:30 | 6 | Room 5 - Wall 4' | measure perpendicular angle with laser (# drawing ref in corner) |  | 0:16
10:31 | 6 | Room 5 - Wall 4 | carry and place full board in position with lifter |  | 2:15
10:33 | 6 | Room 5 - Wall 4 | Drill board to studs | 11 vertical nails X 3 studs, 4 nails on top and 4 bottom | 4:52
10:38 | 6 | Room 5 - Wall 4 | Cut bottom track |  | 13:08
10:51 | 6 | Room 5 - Wall 4 | Cut wooden reinforcement for door and dintel horizontals studs one section of wood and one regular and drill them together, cut bottom track for section B (other wall) |  | 2:07
10:53 | 6 | Room 5 | Pause to exampain stuff to us |  | 2:01
10:55 | 6 | Room 5 - Wall 4' | Measure and cut board |  | 2:20
10:57 | 6 | Room 5 - Wall 4' | Place first side board and drill |  | 1:06
10:58 | 6 | Room 5 - Wall 4' | Measure and cut second layer side one |  | 0:55
10:59 | 6 | Room 5 - Wall 4' | Place and drill second layer side one |  | 2:24
11:02 | 6 | Room 5 - Wall 4' | Place and drill auxiliar section of board to aid in the perpendicularity of the corner |  | 0:33
11:02 | 6 | Room 5 - Wall 4 | Drill studs to floor |  | 7:46
11:10 | 6 | Room 5 - Wall 4 | Place vertical studs, 2 tipical, 2 wooden and place top track |  | 6:09
11:16 | 6 | Room 5 - Wall 4 | Measure dintel height on door and place already made dintel and two small studs on dintel | use level | 0:52
11:17 | 6 | Room 5 - Wall 4 | Mark and cut board first side |  | 5:34
11:23 | 6 | Room 5 - Wall 4 | Place on position with lifter and drill full board | rework take out 4 ails | 0:50
11:24 | 6 | Room 5 - Wall 4 | Cut with saw the section of the door from that side |  | 1:19
11:25 | 6 | Room 5 - Wall 4 | Measure dintel on wall and then measure and cut second board |  | 0:28
11:25 | 6 | Room 5 - Wall 4 | Place full board with lifter |  | 2:33
11:28 | 6 | Room 5 - Wall 4 | Drill board to studs |  | 3:45
11:32 | 6 | Room 5 - Wall 4 | Cut out door portion of the board |  | 0:49
11:32 | 6 | Room 5 - Wall 4 | Rework: fix corner with sand |  | 2:43
11:35 | 6 | Room 5 | Clean up
11:36 | 6 | Room 5 - sector A done
LAYOUT
13:22 | 7 | Room 1 | Layout chalkline, measure and mark doors | 2 workers | Start timelapse video at 13:23
13:26 | 7 | Room 1 | Spray paint | main marks on floor already done as reference
13:27 | 7 | Room 1 | Done |  | Finished timelapse
7
13:35 | 7 | Room 5 | Layout chalkline, measure and mark doors, spray |  | Start timelapse
13:43 | 7 | Room 5 | Done |  | Finished timelapse
7
13:45 | 7 | Room 6 | Layout chalkline, measure and mark doors, spray |  | Start timelapse
13:51 | 7 | Room 6 | Done | In 20 minutes finished all rooms (1-6) but room 4 - already done the day before | Finished timelapse
14:56 | 7 | Room 4 | Set up electric work on room, move materials | 1 worker | Start timelapse
15:10 | 7 | Room 4 | Finish set up materials |  | Finished timelapse
Get timelapse from another sim card

## Day 3 - 27 March
Day 3 March 27 videos
video 9 | https://www.youtube.com/watch?v=lcDRlKGUqnE |  |  | final video of the day boxes on front wall
video 10 | https://www.youtube.com/watch?v=pNURGHT95fg |  |  | previo to video 9 backing on front wall
video 11 | https://www.youtube.com/watch?v=L9FhSurluXU |  |  | room 6
video 12 | https://www.youtube.com/watch?v=t_KMxK3-OIY |  |  | enebrating morning 2
video 13 | https://www.youtube.com/watch?v=2QY2Ldqp84c |  |  | enebrating morning 1
video 14 | https://www.youtube.com/watch?v=0G0d16sC4f8
Time | Level | Location | Task | Site Observations | Recording observations / duration | General observations
7:21 | 6 | Room 4 | Start measuring and drill holes on drywall with circular drill for electrical boxes |  | Start timelapse 1 7:17
7:37 | 6 | Room 4 | Open electrical boxes, join together a couple, attach to white finish plastic
7:44 | 6 | Room 4 | Glue each box w/ silicon gun and start placing them in position | use level to make sure they are straight, missing high resistance boxes for shaft wall - will have to come back to those after lunch
7:56 | 6 | Room 4 | Start making holes on studs for electrical cable tube (grey) and enebrar between boxes
9:00 | 6 | Room 4 | Break |  | Finish first timelapse
9:30 | 6 | Room 4 | Continue enhebrating
9:51 | 6 | Room 4 | Continue enhebrating , places white fixers to wall around grey cables and drill them | Ventilation and electrical clash, hard to pass cable - from shaft to kitchen, lost a few minutes | Start timelapse 2
10:42 | 6 | Room 4 | Done electrical work all but shaft wall boxes |  | Finish timelapse 2
11:13 | 6 | Room 6 | Measure and mark wall 1 of L in the room, drill holes for boxes, glue boxes and position an glue | Boxes already joined | Start timelapse 3
11:41: AM | 6 | Room 6 | Finished sector wall 1 - start sector 2 in the room starting with the 'tablero'
12:00 | 6 | Room 6 | Lunch break
13:17 | 6 | Room 4 | Start finishing shaft wall missing before, cut 2 boards sections for backing drill them to studs in the main wall |  | Start timelapse 4
13:20 | 6 | Room 4 | Get boxes and separate them start gluing them, use guide to level both boxes that need to be on the same side
13:38 | 6 | Room 4 | Start to enhebrate and secure cables with precinto
13:47 | 6 | Room 4 | Done electrical work on room 4, start clean up and move materials
13:51 | 6 | Room 4 | Room cleared and finished | No inspection needed on electrical work to close the wall | Finish timelapse 4

## Day 4 - 28 March
Day 4 March 28 videos
video 15 | https://youtu.be/V5ZtbSl2xP4
video 16 | https://youtu.be/CtQ1kVjjxzY
video 17 | https://youtu.be/FWGwzsbc6OU
video 18 | https://youtu.be/KX7tgvlvsak
video 19 | https://youtu.be/0ULGttuLYPY
Time | Level | Location | Task | Site Observations | Recording observations / duration | General observations
7:00 | 5 | Room 4 - wall 2 | Get and cut metallic backing for kitchen wall |  | Timelapse 1 starts 7:10:36
7:13 | 5 | Room 4 - wall 2 | Measure and cut wood backing
7:15 | 5 | Room 4 - wall 2 | Marck and measure on wall 2, put nails for support
7:18 | 5 | Room 4 - wall 2 | go find backing metallic and bring to wall 2
7:19 | 5 | Room 4 - wall 2 | place on wall metallic backing two long ones and a short one on top
7:31 | 5 | Room 4 - wall 7 | drill wooden one inside room B for cabinet
7:35 | 5 | Room 4 | explain something to me
7:38 | 5 | Room 4 - wall 7 | place metal backing on room B
7:46 | 5 | Room 4 - wall 7 | measure and cut drywall board
7:50 | 5 | Room 4 | coordination with manager and another crew member from drywall side 2 | Problem with finishes of prefab kitchen door when it stands against the one done manually they don’t align, to fix it will need to take out one layer and tilt it accordingly |  | Theres information sheet on wall with the specifications for that room - might need different kitchen, backings, specs, even though the workers know each room they have to check that spreadsheet just in case. When they start the work they divided odds and even room numberrs among the crew and they repeat that one in each floor.
7:59 | 5 | Room 4 - wall 7 | Place and drill first section of walls, place wood backings
8:11 | 5 | Room 4 - wall 7 | Place and drill new board - full board
8:14 | 5 | Room 4 - wall 7 | Bring new board, place it and drill, use lift board tool |  |  | 12 vertical and 5 horizontals approx
8:23 | 5 | Room 4 - wall 7 | Go pick up next board
8:23 | 5 | Room 4 - wall 7 | Mark and cut board - final section of wall 7 |  |  | www.gyproc.com board brand
8:25 | 5 | Room 4 - wall 7 | Bring board to position |  |  | GYPROC GNE 13 normal ERGO
8:25 | 5 | Room 4 - wall 7 | Place and drill | Worker drills top half of wall 7 by board section, one by one, and then all the bottom together
8:27 | 5 | Room 4 - wall 7 | Drill bottom half of 4 boards wall 7
| 5 | Room 4 - wall 7 | Finished sector 4 | 8:28
| 5 | Room 4 - wall 7 | Finished sector 3 | 8:28
| 5 | Room 4 - wall 7 | Finished sector 2 & 1. Rework take 1 nail out | 8:31
8:33 | 5 | Room 4 - wall 2 | Measure on wall
8:35 | 5 | Room 4 - wall 2 | Measure and cut board, mark positions for ventilation & boxes, cut them already in table with special circular drill that make precise holes, rectangular cuttings done with saw
8:45 | 5 | Room 4 - wall 2 | Move board to position
8:46 | 5 | Room 4 - wall 2 | Place on position with lifter
8:47 | 5 | Room 4 - wall 2 | Use auxiliary wooden frame to hold board in position and drill board just to the metalic backing (needs extra screws) Rework: take out 1 screw
8:53 | 5 | Room 4 - wall 2 | Measure rest of wall
8:54 | 5 | Room 4 - wall 2 | Measure and mark board
8:56 | 5 | Room 4 - wall 2 | Drill holes on board on top of the table - need different drilling sizes - change drill bits
8:58 |  |  | Break | Finish timelapse 1
9:30 |  |  | Surveys for workers until 10
10:08 | 5 | Room 4 | Worker still not there - check on video in which minute got in | Start timelapse 2
10:20 | 5 | Room 4 - wall 2 | Finish drilling section 3 of wall, measure for section 4
10:20 | 5 | Room 4 - wall 2 | mark and cut board - section 4
10:23 | 5 | Room 4 - wall 2 | Place board and drill use special magnet to drill on top of the circular electric box (designed to detect the box and drill precisely that circular section out without damaging the box). Rework: take out 5 nails, drill on other sectors of wall 2 to reinforce it
10:38 | 5 | Room 4 - wall 5 | Start measuring wall 5 with door sector
10:40 | 5 | Room 4 - wall 5 | Mark and cut drywall and sand it
10:41 | 5 | Room 4 - wall 5 | Move board to position - almost full board in terms of weight and time to carry it
10:42 | 5 | Room 4 - wall 5 | Place wall on wall with lifter and secure it in position
10:44 | 5 | Room 4 - wall 5 | drill board to studs, change drill battery | battery lasts about 6 hrs, better than cable cord drill
10:48 | 5 | Room 4 - wall 5 | measure and cut board first half of door, this worker usually cuts in the table and then place the board on the wall
10:55 | 5 | Room 4 - wall 5 | move board to position
10:55 | 5 | Room 4 - wall 5 | place on wall and secure with lifter
10:57 | 5 | Room 4 - wall 5 | drill to studs, use magnet to make hole for electric box
11:02 | 5 | Room 4 | coordination with the other crew member drywall layer 2, worker running out of boards, not sure how they will bring more to the project
11:06 | 5 | Room 4 - wall 5 | measure board and cut and sand, mark the door | when the side of the door is too thin he would prefer to cut in place, but if not cut in table more precisely
11:11 | 5 | Room 4 - wall 5 | move to position
11:11 | 5 | Room 4 - wall 5 | secure in place and sand border to fix it
11:15 | 5 | Room 4 - wall 5 | drill to wall
11:19 | 5 | Room 4 - wall 1 | measure wall 1 and put magnets on boxes
11:23 | 5 | Room 4 - wall 1 | mark and cut wall boards
11:24 | 5 | Room 4 - wall 1 | move to position
11:25 | 5 | Room 4 - wall 1 | place and secure with lifter - closer to position of drywall table
11:25 | 5 | Room 4 - wall 1 | drill and use magnets - magnets not working very well need to do hole manually for boxes
11:33 | 5 | Room 4 - wall 1 | measure if section 1 in this wall was plumb
11:34 | 5 | Room 4 - wall 1 | grab full board wall of shaft
11:34 | 5 | Room 4 - wall 1 | secure in place
11:35 | 5 | Room 4 - wall 1 | drill to studs, rework: take out one nail
11:36 | 5 | Room 4 - wall 1 | measure last section wall 1 go find section for last piece next door
11:37 | 5 | Room 4 - wall 1 | place on table to measure and cut
11:39 | 5 | Room 4 - wall 1 | Re cut to fix dimention rework
11:40 | 5 | Room 4 - wall 1 | place and secure
11:40 | 5 | Room 4 - wall 1 | drill board
11:42 | 5 | Room 4 - wall 1 | coordinate to move materials next door for room 5 - needs boards side 2 drywall
11:48 | 5 | Room 4 - wall 1 | finish moving | finish timelapse 2
11:51 | 5 | Room 4 - wall 1 | coordinate with electrician
12:00 | 5 | Room 4 - wall 1 | Lunch break
12:39 | 5 | Room 4 - wall 1 | Drill second layer of wall shaft | start timelapse 3 | requires 3 layers total | for fire protection
12:57 | 5 | Room 4 - wall 1 | second layer finished | check what happened in time lapse - got back to the room and wall 1 second layer finished
`12:59:10 | 5 | Room 4 - wall 4 | measure on wall
13:03 | 5 | Room 4 - wall 4 | place board on studs ans drill - door section wall |  |  | there is no stud work for the second layer - all done during the first l
13:03 | 5 | Room 4 - wall 4 | measure in wall and then go cut auxiliary wood section
13:05 | 5 | Room 4 - wall 4 | Drill wall section 1 of door, Use magnet to drill boxes
13:09 | 5 | Room 4 - wall 4 | Cut two wooden sections and drill them behind the door dintel | door needs in total 3 backings one in each top corner and one in the middle where the 900mm panels meet to be able to drill them
13:15 | 5 | Room 4 - wall 4 | go find metal backing for bathroom outer zocalos and place them in wall
13:23 | 5 | Room 4 - wall 4 | bring full panel
13:25 | 5 | Room 4 - wall 4 | put it in place
13:27 | 5 | Room 4 - wall 4 | drill - rework: take out 4 screws
13:31 | 5 | Room 4 - wall 4 | measure in wall for metalic backing , cut backing in hallway and drill the backing | backing is stored in the hallway to share among the workers in the floor and not move it around between rooms
13:37 | 5 | Room 4 - wall 4 | measure on wall for wood backing - cut backing
13:52 | 5 | Room 4 - wall 4' | place wall 4' behind bathroom see drawing
14:00 | 5 | Room 4 - wall 4 | place second backing and measure for second side of door | hanger outside of bathroom - don't know the exact height so have to place vertical backing in the whole section
14:04 | 5 | Room 4 - wall 4 | measure and cut board | workers complained that prefab walls didn’t optimize the number of panels on the outside to the 900mm of boards - see picture
14:08 | 5 | Room 4 - wall 4 | place in position
14:09 | 5 | Room 4 - wall 4 | drill - rework: take out 10 nails
14:18 | 5 | Room 4 - wall 4 | mark and cut board for last section wall 4
14:22 | 5 | Room 4 - wall 4 | place board and drill
14:30 | 5 | Room 4 - wall 6 | measure wall and cut board
14:36 | 5 | Room 4 - wall 6 | place 1 section of board on wall
14:36 | 5 | Room 4 - wall 6 | drill board to studs
14:38 | 5 | Room 4 - wall 6 | cut and place second board
14:40 | 5 | Room 4 - wall 6 | drill board to studs
14:46 | 5 | Room 4 - wall 6 | adjust with saw the border of wall
14:48 | 5 | Room 4 - wall 6 | measure in wall, measure and cut board
14:54 | 5 | Room 4 - wall 6 | Place drywall board - full
14:54 | 5 | Room 4 - wall 6 | Drill, rework: take out one nail
15:01 | 5 | Room 4 - wall 6 | Cut with saw profile of door in wall itself | side of door was too narrow to cut in table
15:03 | 5 | Room 4 - wall 1 | set and place full board second layer
15:06 | 5 | Room 4 - wall 4 | Measure second section
15:06 | 5 | Room 4 - wall 1 | Drill first section
15:08 | 5 | Room 4 - wall 4 | Grab and cut section of board
15:09 | 5 | Room 4 - wall 4 | Place layer 2 in position for another section wall 4
15:10 | 5 | Room 4 - wall 4 | Make holes for electrical boxes
15:12 | 5 | Room 4 - wall 4 | Coordinate and move boards to next room
15:17 | 5 | Room 4 - wall 4 | Continue drilling wall 4
15:18 | 5 | Room 4 | Done finish timelapse
Wall 3 to be finished on the next day - probably wit the half an hour lost in the survey it could have been finished on the same day
Day summary |  |  |  |  | Progress until noon
Layer 2 of drywall working on level 5 rooms 4 & 5, worker from drywall layer 1 went down to help and started room 1 |  |  |  |  | Level 9 | layout done
Electrical work on level 6, room 5 |  |  |  |  | Level 8 | layout done
Layer 1 of drywall on level 7 |  |  |  |  | Level 7 | drywall layer 1 room 1, rest just layout
Level 4 - no activity today |  |  |  |  | Level 6 | Electrical work done in all but rooms 5, 3 in progress, drywall layer 1 done
Level 3 - no activity |  |  |  |  | Level 5 | Rooms 4, 5, and 1 work in progress layer 2 drywall, electrical work done,
Level 2 - no activity |  |  |  |  | Level 4 | drywall second layer finished
[5 empty] | Level 3 | drywall second layer finished
[5 empty] | Level 2 | paint finished and corners
After luch observed sheet rock insulation in wall levrl 7 - room 1: crew from drywall side 1
for warm and noise in opening to the hall of the other building - opening of approx 100 x 2,10
12:42 | 7 | Room 1 | cut insultation
12:44 | 7 | Room 1 | place between studs
12:47 | 7 | Room 1 | go get drill
12:48 | 7 | Room 1 | measure on wall and place glue between studs
12:48 | 7 | Room 1 | place studs 1 bottom 1 top and two verticals on inner side - drill to concrete | wall needs second layer for fire
12:50 | 7 | Room 1 | done
next step is to place two more vertical studs, place again sheet rock between them and drill board from the inside
see picture of profile
Next steps in the order after wall is done both sides:
1) cover nails in wall: painter crew 2 parallel crews
2) corners: 1 crew member different from painter
3) ventilation subcontractor pipes
4) back to drywall to cover piepes last step with the walls already finished just around the pipes

## summary
| Productivity apt 4 | Productivity apt 6 | Productivity apt 5 | Average | Productivity of door type | productivity of ducts | Productivity of plain walls | Productivity of walls with 3 layers
Layout | 0.6 min / ml | 0.43 min / ml | 0.35 min / ml | 0.46 | 9.837 | 14.4 | 6.66 | 11.8867
walls sqm side 1 | 24.5 | 37.6 | 22.7
Drywall side 1 | 5.68 min / sqm | 6.9 min / sqm | 6.5 min / sqm | 6.36
walls sqm side 2 | 48.57
Drywall side 2 | 8.4 min / sqm |  |  | 8.4
Electrical | 6.09 min / sqm | 6.09 min / sqm |  | 6.09
Insulation | 28.9 min / sqm |  |  | 28.9
Non value adding tasks (coordination, rework, find materials) | 1.6 min / sqm = 28% drywall 1 0.2 min /sqm = 3.2% electrical 0.85min / sqm = 10% drywall 2 | 3.06 min / sqm = 20% drywall 1 0.2 min /sqm = 3.2% electrical | 0.26 min / sqm = 4% drywall 1
Average | cut board = total 52.15 minutes | full board = total 46.81 minutes |  | total for 2 sides of wall
Layout | 0.46 | 0.46 |  | 14.76 | min/sqm | company average: 24.6 min/sqm
Re do layout on wall | 7.5 | 7.5
Place bottom / top track | 4.1 | 4.1 |  | 12.72 | following fastest time | almost half of company average
Place vertical studs stud | 3.05 | 3.05
measure on wall | 1.65
Measure and cut board | 3.75
Move board to position | 0.27 | 0.33
secure board and drill to studs | 5.5 | 5.5
electrical | 14.7 | 14.7
measure on wall | 1.65 | 1.65
Measure and cut board | 3.75 | 3.75
Move board to position | 0.27 | 0.27
place and drill board side 2 | 5.5 | 5.5
total | 52.15 | 46.81
| Productivity apt 4 | Productivity apt 6 | Productivity apt 5 | Average | Door opening | Duct wall | Plain wall | Three-layered wall
Layout | 0.6 min / ml | 0.43 min / ml | 0.35 min / ml | 0.46 | 9.837 | 14.4 | 6.66 | 11.8867
Drywall side 1 | 5.68 min / sqm | 6.9 min / sqm | 6.5 min / sqm | 6.36
Drywall side 2 | 8.4 min / sqm |  |  | 8.4
Electrical | 6.09 min / sqm | 6.09 min / sqm |  | 6.09
Insulation | 28.9 min / sqm |  |  | 28.9
Non value adding tasks (coordination, rework, find materials) | 1.6 min / sqm = 28% drywall 1 0.2 min /sqm = 3.2% electrical 0.85min / sqm = 10% drywall 2 | 3.06 min / sqm = 20% drywall 1 0.2 min /sqm = 3.2% electrical | 0.26 min / sqm = 4% drywall 1
Productivity per room | Apartment 4 | Apartment 6 | Apartment 5 | Average
Drywall side 1 | 5.68 | 6.9 | 6.5 | 6.36
Drywall side 2 | 8.4 |  |  | 8.4
Electrical | 6.09 | 6.09
[7 empty] | Non adding value tasks (h) | Adding value tasks (h) | Total task (h) | Percent
[6 empty] | Drywall side 1 | 0.65 | 1.67 | 2.32 | 0.28017
[6 empty] | Drywall side 2 | 0.688 | 6.112 | 6.8 | 0.10118
[6 empty] | Total | 1.338 | 7.782 | 9.12 | 0.14671

## summary (2) (hidden)
Average | cut board = total 52.15 minutes | full board = total 46.81 minutes
Layout | 0.46 | 0.46
Re do layout on wall | 7.5 | 7.5
Place bottom / top track | 4.1 | 4.1
Place vertical studs stud | 3.05 | 3.05
measure on wall | 1.65
Measure and cut board | 3.75
Move board to position | 0.27 | 0.33
secure board and drill to studs | 5.5 | 5.5
electrical | 14.7 | 14.7
measure on wall | 1.65 | 1.65
Measure and cut board | 3.75 | 3.75
Move board to position | 0.27 | 0.27
place and drill board side 2 | 5.5 | 5.5
total | 52.15 | 46.81
| Productivity apt 4 | Productivity apt 6 | Productivity apt 5 | Average Productivity | Door opening | Duct wall | Plain wall | Three-layered wall
Layout | 0.6 min / ml | 0.43 min / ml | 0.35 min / ml | 0.46 | 9.837 | 14.4 | 6.66 | 11.8867
Drywall side 1 | 5.68 min / sqm | 6.9 min / sqm | 6.5 min / sqm | 6.36
Drywall side 2 | 8.4 min / sqm |  |  | 8.4
Electrical | 6.09 min / sqm | 6.09 min / sqm |  | 6.09
Insulation | 28.9 min / sqm |  |  | 28.9
Non value adding tasks (coordination, rework, find materials) | 1.6 min / sqm = 28% drywall 1 0.2 min /sqm = 3.2% electrical 0.85min / sqm = 10% drywall 2 | 3.06 min / sqm = 20% drywall 1 0.2 min /sqm = 3.2% electrical | 0.26 min / sqm = 4% drywall 1
Productivity per room | Apartment 4 | Apartment 6 | Apartment 5 | Average
Drywall side 1 | 5.68 | 6.9 | 6.5 | 6.36
Drywall side 2 | 8.4 |  |  | 8.4
Electrical | 6.09 | 6.09
Percent
0.28017
0.10118
0.14671
| Non adding value tasks (h) | Adding value tasks (h) | Total task (h)
Drywall side 1 | 0.65 | 1.67 | 2.32
Drywall side 2 | 0.688 | 6.112 | 6.8
Total | 1.338 | 7.782 | 9.12